{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":71,"n_cols":6,"rows_kept":71,"cut":false,"hidden":false,"merged":[[54,1,67,1],[0,0,0,5],[1,0,1,5],[2,1,30,1],[43,1,53,1],[31,1,42,1]],"flags":["formulas_cached_only"]}
["附件5"]
["                 2023年学校迎新工作具体事务日程表"]
[1,"筹备阶段","日期","负责部门","工作内容","负责人（对接）"]
[2,null,"2023-08-25","学生工作处 团委","召集召开迎新协调会","姜利波"]
[3,null,"26日","各部门(单位）","14:00前就工作方案反馈意见","唐成人"]
[4,null,"27日","各部门(单位）","核对及上报志愿者补助人数（二级学院按录取人数10%），9月3日前报名单及卡号","麻世平"]
[5,null,"27日","学生工作处  团委、相关学院","完成老生调寝及系统信息更新工作","张文博、孙明钦、王彦俊"]
[6,null,"27日","各部门（单位）","将迎新需桌椅数报后勤保卫处、普湾管理办公室","杜枢、姜淑燕、杨守国"]
[7,null,"27日","学生工作处  团委","完成新生公寓分配","唐成人、张文博、唐爱琴、王彦俊"]
[8,null,"27日","财务处","已缴费新生配送票据","孙宏鑫"]
[9,null,"27日","招生与就业处","新生数据导入学生工作系统","宋佳"]
[10,null,"28日前","各学院","下班前报送各学院《迎新工作安排表》","麻世平"]
[11,null,"28日前","学生工作处、创新创业学院","《学生手册》、《素质教育评估手册》、校徽、床位卡等新生物品发放","赵静、张文博、孙明钦、王彦俊"]
[13,null,"28日前","后勤保卫处、普湾管理办公室","完成B5、B3、C5等宿舍楼改造施工","董秀勇、姜淑燕、太清立"]
[14,null,"28日","学生工作处  团委","新生辅导员培训","张海鑫、杜智勇、麻世平"]
[15,null,"28日","学生工作处  团委","校园网发布迎新工作实施方案","张文博"]
[16,null,"28日","学生工作处  团委","完成军训部队对接，做好准备工作","麻世平、王彦俊、孙明钦"]
[17,null,"28日","各部门（单位）","将迎新工作牌数、迎新用水数量报团委","唐成人"]
[18,null,"29日前","现教中心","三校区迎新现场网络和学生系统测试","10:00，各学院新生辅导员参加"]
[19,null,"29日前","各学院","完成新生寝室清扫工作"]
[21,null,"29日前","现教中心","夏家河、南关岭校区、普湾校区校园卡提前发放至各二级学院"]
[22,null,"30日前","后勤保卫处、普湾管理办公室","9：00前，完成迎新现场电源设置"]
[23,null,"30日前","后勤保卫处、普湾管理办公室","向各部门（单位）发放桌椅"]
[24,null,"30日前","学生工作处  团委","向各部门（单位）发放工作牌"]
[25,null,"30日前","学生工作处  团委","志愿者选拔和培训结束"]
[26,null,"30日前","后勤保卫处、普湾管理办公室","安排好新生饮食、洗浴等事宜"]
[27,null,"31日前","各部门（单位）","15:00前，完成迎新场地布置"]
[28,null,"31日前","后勤保卫处、普湾管理办公室、学生工作处 团委","完成迎新接站准备"]
[29,null,"31日前","后勤保卫处、普湾管理办公室","完成警力支援联络工作"]
[32,null,"1日前","学生工作处 团委、各学院","6:00前，迎新氛围营造完成"]
[33,null,"9日前","办公室","完成夏家河校区体育场音响设置和调试工作"]
[34,"报到阶段","1日前","各部门（单位）","提前报到学生妥善安置"]
[35,null,"1日","后勤保卫处、普湾管理办公室","班车安排"]
[36,null,"1日","后勤保卫处、普湾管理办公室","大连站、大连北站、金普高铁站、普兰店站、客运站、机场接站工作"]
[37,null,"1日","学生工作处 团委","接站志愿者安排到位"]
[38,null,"1日","后勤保卫处","4:50，夏区南门岗安排车辆接迎新志愿者到大连站、机场"]
[40,null,"1日","后勤保卫处、普湾管理办公室","医疗服务"]
[41,null,"1日","学生工作处  团委","寝室调配"]
[42,null,"1日","学生工作处  团委","绿色通道"]
[43,null,"1日","学生工作处  团委","军训服发放"]
[44,null,"1日","后勤保卫处、普湾管理办公室","入校管理、安全保卫、交通疏导"]
[45,null,"1日","现教中心","网络保障、系统指导、校园卡事宜"]
[47,null,"1日","各学院","报到新生接待；组织新生辅导员佩戴校徽等"]
[48,"入学教育","2-3日","后勤保卫处、普湾管理办公室","安全教育"]
[49,null,"2-3日","办公室","夏校区俱乐部使用保障"]
[50,null,"2-3日","后勤保卫处","南校区俱乐部使用保障"]
[51,null,"2-3日","现教中心","两校区入学教育多媒体使用保障"]
[52,null,"2-3日","普湾管理办公室","普湾校区入学教育多媒体使用保障"]
[53,null,"2-3日","各学院","入学教育"]
[54,null,"2-3日","教务处","入学教育教室保障"]
[55,null,"2日—30日","创新创业学院、各二级学院","素质教育课程宣贯"]
[56,null,"2日—30日","各学院","入学教育"]
[57,null,"26日","各学院","向学生工作处报送《学生手册》、《素质教育课程培养过程与评估手册》考试试卷","王彦俊"]
[58,null,"30日前","各学院","《学生手册》、《素质教育课程培养过程与评估手册》考试结束，承诺书存档至各学院"]
[59,"军训","10日","后勤保卫处","山上体育场临时卫生间租赁到位"]
[60,null,"10日","学生工作处  团委、后勤保卫处","8:30到驻地接教官","王彦俊"]
[61,null,"10日","学生工作处  团委","11:00，教官到校后住宿安置、用餐安排"]
[62,null,"10日下午","后勤保卫处、普湾管理办公室","14:00，医疗服务到位"]
[63,null,"10日下午","后勤保卫处、普湾管理办公室","C区体育场卫生间开放；普湾体育场开放"]
[64,null,"10日下午","办公室","训练场音响保障"]
[65,null,"10日下午","后勤保卫处","负责军训场地安全保卫工作"]
[66,null,"10日下午","各二级学院","军训动员大会，军事技能训练"]
[67,null,"19日.20日","后勤保卫处","南校区、普湾校区学生彩排车辆保障"]
[68,null,"22日","宣传统战部","开学典礼影像拍摄"]
[69,null,"22日","学生工作处  团委","开学典礼、汇报表演"]
[70,null,"22日","学生工作处  团委","迎新晚会"]
[71,null,"22日","后勤保卫处","运送南关岭校区、普湾校区新生车辆安排（往返）"]
[72,null,"22日晚或23日","后勤保卫处","8:30，安排车辆送教官回部队驻地"]
[73,"体检","14日-17日","后勤保卫处","由后勤保卫处具体安排"]
[74,"领取教材","2日.3日","教务处","由教务处具体安排"]
[75,"入馆教育","2日-30日","图书馆","由图书馆具体安排"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}