{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":72,"n_cols":6,"rows_kept":72,"cut":false,"hidden":false,"merged":[[0,0,0,5],[1,0,1,5],[2,1,31,1],[32,1,44,1],[45,1,54,1],[55,1,68,1]],"flags":["formulas_cached_only"]}
["附件5"]
["                 2025年学校迎新工作具体事务日程表"]
[1,"筹备阶段","日期","负责部门","工作内容","负责人（对接）"]
[2,null,"9月1日","学生工作处 团委","召集召开迎新协调会","姜利波"]
[3,null,"9月1日","各部门(单位）","14:00前就工作方案反馈意见","姜利波"]
[4,null,"9月2日","各部门(单位）","核对及上报志愿者补助人数（二级学院按录取人数10%），9月9日前报名单及卡号","晏佳羽"]
[5,null,"9月2日","学生工作处  团委、相关学院","完成老生调寝及系统信息更新工作","张文博、孙明钦、王彦俊"]
[6,null,"9月2日","各部门（单位）","将迎新需桌椅数报后勤保卫处、普湾管理办公室","杜枢、兰全日、杨守国"]
[7,null,"9月2日","学生工作处  团委","完成新生公寓分配","张文博、孙明钦、王彦俊"]
[8,null,"9月2日","财务处","已缴费新生配送票据","孙宏鑫"]
[9,null,"9月2日","招生与就业处","新生数据导入学生工作系统","何毅"]
[10,null,"9月2日","后勤处","夏家河校区助理辅导员关于智慧食堂使用培训","厉伟"]
[11,null,"9月2日","后勤处","智慧食堂宣传视频拍摄，学工团委公众号推送","厉伟"]
[12,null,"9月3日","各学院","当日下班前报送各学院《迎新工作安排表》","王巧"]
[13,null,"9月3日","学生工作处、创新创业学院","《学生手册》、校徽、床位卡等新生物品发放","赵静、张文博、孙明钦、王彦俊"]
[14,null,"9月3日","后勤处、普湾校区管理办公室","完成新生入住宿舍准备工作","太清立、姜树燕、杜枢"]
[15,null,"9月3日","学生工作处  团委","新生辅导员培训","姜利波、张文博、张海鑫、冯香琴"]
[16,null,"9月3日","学生工作处  团委","校园网发布迎新工作实施方案","张文博"]
[17,null,"9月3日","学生工作处  团委","完成军训部队对接，做好准备工作","张文博、王彦俊、孙明钦"]
[18,null,"9月3日","各部门（单位）","将迎新工作牌数、迎新用水数量报团委","王巧"]
[19,null,"9月4日","各学院","完成新生寝室清扫工作"]
[20,null,"9月4日","现教中心","做好虚拟校园卡激活和使用的准备及培训指导工作","夏家河：谢沛阳；普湾：高强；南关岭：梅韶南"]
[21,null,"9月5日","后勤处、普湾校区管理办公室","9：00前，完成迎新现场电源设置","杜枢、兰全日、杨守国"]
[22,null,"9月5日","后勤处、普湾校区管理办公室","向各部门（单位）发放桌椅","杜枢、兰全日、杨守国"]
[23,null,"9月5日","学生工作处  团委","向各部门（单位）发放工作牌","王巧"]
[24,null,"9月5日","学生工作处  团委","志愿者选拔和培训结束","晏佳羽"]
[25,null,"9月5日","后勤处、普湾校区管理办公室","安排好新生饮食、洗浴等事宜","太清立、姜树燕、杜枢"]
[26,null,"9月5日","各部门（单位）","15:00前，完成迎新场地布置"]
[27,null,"9月5日","后勤处、普管办、学生工作处 团委","完成迎新接站准备"]
[28,null,"9月5日","后勤处、安全保卫处、普湾校区管理办公室","完成警力支援联络工作"]
[29,null,"9月6日","学生工作处 团委、各学院","6:00前，迎新氛围营造完成"]
[30,null,"2025-09-07","办公室","上午前完成夏家河校区体育场音响设置和调试工作"]
[31,"报到阶段","2025-09-05","各部门（单位）","提前报到学生妥善安置"]
[32,null,"9月6日","后勤处、普湾校区管理办公室","班车安排"]
[33,null,"9月6日","后勤处、普湾校区管理办公室","大连站、大连北站、金普高铁站、普兰店站和客运站、机场接站工作"]
[34,null,"9月6日","学生工作处 团委","接站志愿者安排到位"]
[35,null,"9月6日","后勤处","4:50，夏区南门岗安排车辆接迎新志愿者到大连站、机场"]
[36,null,"9月6日","普湾校区管理办公室","05:30，普湾校区南院大门岗安排车辆接迎新志愿者到金普站、普兰店站和客运站"]
[37,null,"9月6日","后勤处","医疗服务"]
[38,null,"9月6日","学生工作处  团委","寝室调配"]
[39,null,"9月6日","学生工作处  团委","绿色通道"]
[40,null,"9月6日","学生工作处  团委","军训服发放"]
[41,null,"9月6日","后勤处、安全保卫处、普湾校区管理办公室","入校管理、安全保卫、交通疏导","史洪河、宋伟官、杨守国"]
[42,null,"9月6日","现代教育技术中心","网络保障、系统指导、校园卡事宜","夏家河：邓少华、张广鑫、谢沛阳；南关岭：张英敏、梅韶南；普湾：高强、刘润龙"]
[43,null,"9月6日","各学院","报到新生接待；组织新生辅导员佩戴校徽等"]
[44,"入学教育","9月6日-7日","后勤处、安全保卫处、普湾校区管理办公室","安全教育"]
[45,null,"9月6日-25日","办公室","夏家河校区俱乐部使用及多媒体保障"]
[46,null,"9月6日-25日","后勤处","南关岭校区俱乐部使用保障"]
[47,null,"9月6日-25日","普管办","普湾校区俱乐部使用保障"]
[48,null,"9月6日-25日","现代教育技术中心","三校区入学教育多媒体使用保障"]
[49,null,"9月6日-25日","教务处","入学教育教室保障"]
[50,null,"9月6日-25日","创新创业学院、各二级学院","素质教育课程宣贯"]
[51,null,"9月6日-25日","各学院","入学教育"]
[52,null,"9月25日","各学院","向学生工作处报送《学生手册》、《素质教育课程培养过程与评估手册》考试试卷","何勇"]
[53,null,"9月27日前","各学院","《学生手册》、《素质教育课程培养过程与评估手册》考试结束，承诺书存档至各学院"]
[54,null,"9月7日","学生工作处  团委、后勤处","07:00到驻地接教官","王彦俊"]
[55,null,"9月7日","学生工作处  团委、后勤处、普管办","11:30，教官到校后住宿安置、用餐安排"]
[56,null,"9月7日-26日","安全保卫处、普管办","夏家河校区和普湾校区体育场开放"]
[57,null,"9月8日-26日","后勤处","7:50至当日军训结束，保障医疗服务"]
[58,null,"9月8日-26日","办公室","训练场音响保障"]
[59,null,"9月8日-26日","后勤处、安全保卫处、普管办","负责军训场地安全保卫工作"]
[60,null,"9月7日","各二级学院","军训动员大会"]
[61,null,"9月8日-26日","各二级学院","军事技能训练"]
[62,null,"9月24日、26日","后勤处、普湾校区管理办公室","南关岭校区、普湾校区学生彩排车辆保障"]
[63,null,"9月26日","宣传统战部","开学典礼影像拍摄"]
[64,null,"9月26日","学生工作处  团委","开学典礼、汇报表演"]
[65,null,"9月26日","学生工作处  团委","迎新晚会"]
[66,null,"9月26日","后勤处、普湾校区管理办公室","运送南关岭校区、普湾校区新生车辆安排（往返）"]
[67,null,"9月27日","后勤处","09:00，安排车辆送教官回部队驻地"]
[68,"体检","16日-19日","后勤处","由后勤处具体安排  普17；南16；夏18、19","郭守平、孔韵如"]
[69,"领取教材","8日-16日","教务处","由教务处具体安排"]
[70,"入馆教育","7日-30日","图书馆","由图书馆具体安排"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}